## Sheet1
Track	PWS	Name	Git	Content(s)	Format(s)	WBS	Section
PM	1AA	Artifact Repository		Project Gits		Q1	8.2
PM	1A	Non-disclosure/Non-Use Agreement				Q1	6.1
PM	1B	Quality Control Plan [QCP]	documents	an effective quality control program		Q1	1.6.1
PM	1C	Phase-out Migration Plan	documents	elaborates the artifacts to be transitioned on the Project Repository, and a schedule for transition completion		Q4	1.6.17
PM	2	Program Management Plan (PMP)	documents	strategy to accomplish the tasks and include the risk, quality and technical management approach, work breakdown structure (WBS), schedule management approach, schedule, cost requirements, and proposed staffing		Q1	5.2
PM	3	Program Schedule and Monthly Updates	documents	schedule, updated monthly		Monthly	5.2
PM	4	Monthly Progress Report		includes project status and financial management reporting		Monthly	5.2
PM	5	Quarterly Strategic Communications Message	documents	project progress and feasibility of transition to production		Quarterly	5.2

A	13	Website	Website	website, infographics to showcase the contents of the VDM and MVDM Subset	HTML, Javascript (d3.js)	Q1 → Q4	5.3.2
A	E3	FileMan TEST VISTA [“nodeVISTA”]	nodeVISTA	a test VISTA (“nodeVISTA”) that hosts different test datasets (“nodeVISTA Scenarios”)	VISTA System, Vagrant	Q1 → Q4
A	E4	Document Generators	documents	Programmer documentation will be generated using tools such as Sphinx (http://sphinx-doc.org/) and JSDoc (http://usejsdoc.org/). Important Markdown-formatted documents need to be translated into PDF and HTML	Various	Q1 → Q3

B	7.1	Machine Processable VISTA Data Model (VDM) “Read Only”	VDM	vdm.jsonld, the native VISTA data model in JSON-LD based on one or more dd.jsonld's. / VDM Maker, a program that creates vdm.jsonld from dd.jsonld's. / This version will support query/read (“VDM (read)”).	JSON-LD, Python, Javascript	Q1	5.3.1
B	7.2	Machine Processable VISTA Data Model (VDM)	VDM	vdm.jsonld, enhanced by write-data in _dd.jsonld_s and rpc.jsonld. / VDM Maker must process more information from dd.jsonld's and process rpc.jsonld.	JSON-LD, Python, Javascript	Q2 → Q4	5.3.1
B	8	Date-stamped FileMan Data Model Implementations (Definitions) (cross refs, triggers ...)	VDM	dd.jsonld, a data dictionary captured in JSON-LD / DDJLD Maker, a program that caches and interprets the dictionaries from VISTAs in JSON-LD form. MUMPS code reduction will be needed for write-back support	JSON-LD, Python, Javascript	Q1 → Q2	5.3.1
B	E1	RPC Model	VDM, nodeVISTA	formal definition of the model implicit in “write-back RPCs”, rpc.jsonld. Required for write support in vdm.jsonld (#7.2/#E2.2). Created with RPCJLD Maker. It may encompass VISTA Options (file 101) too	JSON-LD, Python	Q1 → Q3
B	E2.1	VDM Package “Read-only”	VDM	a package that implements the VDM inside a VISTA. It will allow any FileMan data to be queried according to the VDM.	Javascript (node.js), MUMPS (KIDS)	Q1
B	E2.2	VDM Package	VDM, nodeVISTA	Will add support for creating, updating and deleting (full CRUD) VISTA Data enabled by a write-back supporting VDM (#7.2). Initial write-back testing (in Q1) will be directly against nodeVISTA (“nodeVISTA Commands”)	Javascript (node.js), MUMPS (KIDS)	Q1 → Q4
B	9	(Document) Approach to “Live VDM” Maintenance of Current State	VDM (Wiki)	In a wiki page, describe ways in which dd.jsonld definitions and hence vdm.jsonld could keep pace with changes in VISTAs	Markdown	Q4	5.3.1
B	15	Date Stamped (Application) Meta Data for lab, surgery and other applications	VDM	Metadata Cacher that queries meta-data using VDM package (Read)	Python, JSON-LD	Q2	5.3.3
B	18	Machine-processable [PIKS] Annotations	VDM	Distinguish patient data from other types of VISTA data in a formal definition piks.jsonld. A VDM PIKS definition enables MVDM PIKS which in turn enables patient-centric security (#28)	JSON-LD	Q2	5.3.4
B	19	Software code [for PIKS]	VDM	PIKS Annotation Generator. Relies on VDM Package (Read) to create a piks.jsonld	Python	Q2	5.3.4
B	25	Prototype query access to VISTA Data against VDM [“FQS”]	VDM	Example Query clients that query (read-only) nodeVISTA using a REST-based FileMan Query Service (FQS) implemented over VDM Package (Read)	Javascript, Python, JSON-LD	Q2	5.4.1
B	33	Prototype Web-Based Query Interface to FileMan [VDM] Data	VDM	FQS Web Client for using VDM Package (Read)	Javascript	Q2 → Q3	5.4.1

C	10.1	Master VISTA Data Model (MVDM) “Read-only”	MVDM	mvdm.jsonld, a formal “MVDM Subset” definition with much of the scope of the VPR RPC which must be formally captured in vpr.jsonld.	JSON-LD	Q1 → Q2	5.3.2
C	10.2	Master VISTA Data Model (MVDM)	MVDM	full CRUD support rounded out for mvdm.jsonld.	JSON-LD	Q2 → Q4	5.3.2
C	11.1	[MVDM over VDM] Heuristic (mapping) code “Read-only” [_MVDM Module_]	MVDM	mapping tables and rules implemented in a MVDM module that delivers a read-only version of MVDM over the VDM Package “Read-only”.	Javascript (node.js), JSON	Q2	5.3.2
C	11.2	[MVDM over VDM] Heuristic (mapping) code [_MVDM Module_]	MVDM	full CRUD support added to MVDM Module (Read).	Javascript (node.js), JSON	Q3 → Q4	5.3.2
C	12	[MVDM] Normalization Reports	MVDM (Wiki)	Documents VDM to MVDM mapping as implemented in Deliverable #11.	Markdown	Q2 → Q4	5.3.2
C	14	Report on [MVDM] Exposure of older models	MVDM (Wiki)	Describe how older, cruder models could be handled in the MVDM	Markdown	Q4	5.3.2
C	28	Prototype Patient-centric Data Security	MVDM	First document and then provide a self- contained prototype (“Patient Security Prototype”) that shows how PIKS- enabled annotations enable patient-centric secure queries. The prototype will enhance FQS and have an example client	Javascript, Markdown	Q3 → Q4	5.4.1
C	35	VISTA Application model(s)/Prototype(s) [Tests]	MVDM	MVDM write back tests (tier 1 through 3), enabled by mvdm.js configurations. Test scenarios for Deliverable #11.	Javascript, Python	Q2 → Q4	5.4.2
C	36	Meta-model(s) [VPR] Prototype(s)	MVDM	Test code that shows how well the MVDM supports VPR (Read-only) convenience methods - read-only side of #35	Javascript, Python	Q2 → Q3	5.4.2

D	32	Prototype Web-based Rules Hub	MVDMmap	Prototype a sharable, crowd source-able mechanism to exchange and grow a library of open, standards-based, validated, and exchangeable transformation rules	Web-based interface	Q3	5.4.1
D	39	Reference model(s)/Prototype(s) [“FHIR Translator”]	MVDMmap	Prototypes that demonstrate mapping from MVDM to FHIR	Javascript and/or other translation rules languages	Q3 → Q4	5.4.2
D	40	Document VISTA-ese vs. FHIR	MVDMmap	Human-readable mapping descriptions	Markdown	Q3 → Q4	5.4.2